## Sheet1
No | Question | Task | Version | Task Type | Responsible | Data Source | Resources | Status
1 | Identification of cancer patients
|  | Identify SNOMED cancer class(es): concept_name | current | Exploration | Christian |  | OMOP Vocabulary/SNOMED. "malignant neoplastic disease", concept_code = 363346000 | Done
|  | Create cancer cohort | current | Coding (SQL) | Ray | OMOP Instance | http://www.ohdsi.org/web/atlas/#/cohortdefinition/923212 | Done
|  | Identify cancer patients in an OMOP instance | current | Testing | Ray | OMOP Instance |  | Done
2 | Identifying primary cancer characteristics: histology, location, grade, staging
2.1 | Identify histology and anatomy | Map ICD-O to SNOMED vocabulary. | 1.0 | Vocabulary | Dmytry, Anna |  | SEER, WHO | QA, completion
|  | ETL diagnosis from cancer registry data to OMOP | 1.0 | ETL | Ray | Cancer Registry |  | In progress
2.2 | Identify stage (pathological and clinical) and grade | Choose vocabulary | 1.1 | Exploration | Michael, Rimma |  | CAP Cancer Protocols: http://www.cap.org/web/home/protocols-and-guidelines There is an ongoing effort to normalize the checklists to SNOMED: https://confluence.ihtsdotools.org/display/iPaLM/Cancer+Synoptic+Subgroup | Done
|  | Model stage and grade in CDM; create data extraction queries | 1.1 | Modeling | Rimma |  | Nebraska Lexicon | Done
|  | Perform mappings of diagnostic features from cancer registry (NAACCR) representation to the chosen vocabulary | 1.1 | Vocabulary | Ben, Rimma, Bob | Cancer Registry | From NAACCR to Nebraska Lexicon | Next
|  | Bring NAACCR, Nebraska Lex, and mappings into vocabulary | 1.1 | Vocabulary | Dmytry, Anna | Cancer Registry | From NAACCR to Nebraska Lexicon | Next
|  | ETL stage and grade from cancer registry data to OMOP | 1.1 | ETL | TBD | Cancer Registry
|  | NLP for stage and grade in EMR notes for recurrences | 3 | Coding |  | EMR
3 | Survival time from diagnosis
3.1 | Identify diagnosis date and 1st cancer occurrence | Model reccurrences in OMOP CDM | 1.0 | Modeling | Rimma |  |  | Done
|  | ETL data, same as 2.1 | 1.0 |  |  | Cancer Registry
|  | Create and test survival queries | 1.0 | Testing | TBD | OMOP CDM
4 | Identifying treatment regimen and response to treatment
|  | Model treatment in CDM | 1.2 | Modeling | Michael, Rimma |  |  | Done
4.1 | Chemo-, immuno-, hormone- therapy | Compare SEER/NCI cancer drug classifications to RxNorm | 1.2 | Vocabulary | Michael, Dmytry, Rachel |  | SEER cancer drugs https://seer.cancer.gov/seertools/seerrx/?drug_direction=UP&regimen_direction=UP&rx_type=drug&drug_field=name&regimen_field=name&drug_offset=0&regimen_offset=0&limit=25&search_mode=&q=&mode= | Next
|  | Create cancer drug regimens in OMOP vocabulary | 2 | Vocabulary | Dmytry, Anna, Rachel |  | NCCN XML Order Templates https://www.nccn.org/professionals/OrderTemplates/Default.aspx | Next
|  | ETL drugs from EMR and group into regimens based on dates. Verify using cancer registry data for 1st occurrence. | 1.2 | Coding | TBD | EMR, Cancer Registry
|  | ETL drugs from EMR and group into regimens based on vocabulary regimens. Verify using cancer registry data for 1st occurrence. | 2 | Coding | TBD | EMR, Cancer Registry
4.2 | Surgery | Choose vocabulary that will provide cancer surgery classifiers (SNOMED) | 1.3 | Vocabulary | Rimma |  | IMO | In progress
|  | Explore ICD-10 procedure codes. How prevalent is this coding? | 1.3 | Vocabulary | Michael |  |  | Next
|  | Bring surgery classification to vocabulary | 1.3 | Vocabulary | Dmytry, Anna |  |  | Next
|  | ETL surgical procedures from EMR and group into regimens based on dates. Verify using cancer registry data for 1st occurrence. | 1.3 | Coding | TBD | EMR, Cancer Registry
4.3 | Radiotherapy | Choose vocabulary | 1.4 | Exploration | Michael |  | NCI | Done
|  | Bring NCI radiotherapy classification into vocabulary | 1.4 | Vocabulary | Michael, Dmytry, Med/Radation Oncology |  | NAACCR https://netforum.avectra.com/eweb/DynamicPage.aspx?Site=NAACCR&WebCode=LoginRequired&ssoToken= | Next
|  | ETL radiation treatments from EMR and group into regimens based on dates. Verify using cancer registry data for 1st occurrence. | 1.4 | Coding | TBD | EMR, Cancer Registry
|  | Choose vocabulary for representing radiation therapy attributes | 2 | Exploration | Michael |  | LOINC version of NAACCR vocabulary https://r.details.loinc.org/LOINC/21943-6.html?sections=Comprehensive
|  | Model radiation therapy attributes in CDM | 2 | Modeling | Rimma
|  | ETL radiation therapy attributes from EMR. | 2 | ETL | TBD | EMR, Cancer Registry
4.4 | Palliative care | Explore domain: use cases; misc physician services. | 1.5 | Exploration | Andrew |  |  | In progress
|  | Choose vocabulary: RxNorm | 1.5 | Vocabulary | TBD
|  | Implement vocabulary: map low level to high level | 1.5 | Vocabulary | TBD
|  | Model palliative care attrivutes in CDM | 1.5 | Modeling | Rimma
|  | ETL palliative date from EMR/cancer registry. | 1.5 | ETL | TBD | EMR, Cancer Registry
4.5 | Identify treatment regimen |  | 2
4.6 | Identify treatment's intent |  | 2
4.7 | Identify response to treatment |  | 2
5 | Identify Recurrence and progression of disease |  | 3